## Traceability Matrix
Traceability Matrix (Red Team)
Prototype Title:
Scope: | Platformer focused around a rabbit-themed character navigating through hazardous zones filled with predators, traps, collectibles, and platforming obstacles.
Repository Link: | https://github.com/OddCardboard/redteam
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned to | Completed? Y/N | Notes (include Name of updater)
Player Character | Movement | Add Controls that moves player horizontally using A and D. | Unreal Engine 5 | Pre-alpha | Pre-alpha | Cedrick Lee | Yes | Movement added, Tested? -Cedrick Lee
| Shield | Add a temporary shield that blocks damage for a second after player has already been hit. (Death zones should still kill) | Unreal Engine 5 | Pre-Alpha | Alpha | Cedrick Lee | Yes | Added 1 second shield upon damage -Nathen Reed
| Jump and Double Jumps | Add a jump that allows players to tap for short jumps and hold for a longer jump. As well a double jump if mid-air. | Unreal Engine 5 | Pre-alpha | Alpha | Cedrick Lee | Yes | Added long/short jump and double jump -Nathen Reed
Player Weapons | Jump Attack | Add an attack that triggeres when landing on top of enemy. | Unreal Engine 5 | Pre-alpha | Pre-alpha | Cedrick Lee | Yes | Jump attack placed within enemy classes. -Nathen Reed
Pickups | Health | Health kits that are collected by player to regain health when needed. | Unreal Engine 5 | Alpha | Alpha | Nathen Reed | Yes | Added player Health Pickups with a temp heart model. -Nathen Reed
| Coins | Collectable coins they stay tracked on UI. | Unreal Engine 5 | Alpha | Beta | Nathen Reed | Yes | Added collectible coins that are tracked between stages, and displayed with a widget. -Nathen Reed
Interactables | Checkpoint | Automatic checkpoints that allow the player to respawn. (Checkpoint during boss section should reset boss timer) | Unreal Engine 5 | Pre-alpha | Alpha | Nathen Reed | Yes | Checkpoint Updated With custom FB. -Nathen Reed
| Death Zones | Areas that will destroy the player or any AI that cross into them. | Unreal Engine 5 | Pre-alpha | Alpha | Nathen Reed | Yes | Big deathzone added that resets player to respawn point. -Nathen Reed
| Level Changing | Areas that send player to next level | Unreal Engine 5 | Alpha | Beta | William Meredith | Yes
Boss | Boss Health | Create a health system for the boss. They lose health but get a shield briefly after taking a hit. | Unreal Engine 5 | Alpha | Final Release | Nathen Reed | Yes | Shield works, may need a bit of tweaking to fling the player on each hit to prevent them from hitting the boss over and over.
| Boss HP Display | Display the boss health over the boss. | Unreal Engine 5 | Alpha | Final Release | Nathen Reed | Yes | Added but may be hidden in final version to fit style
| Boss defeat. | Boss is defeated after health reaches zero. | Unreal Engine 5 | Alpha | Final Release | Nathen Reed | Yes | added, requires a win screen post win.
Enemies | Enemy HP | Add HP for each enemy that ticks down if hit by the player. | Unreal Engine 5 | Pre-alpha | Alpha | William Meredith | Yes
| Enemy Death | Enemies should be destroyed when hit by player | Unreal Engine 5 | Pre-alpha | Alpha | William Meredith | Yes
| Enemy triggering | Enemies should spot the player if they get close. Melee enemies should chase after the player to attack. | Unreal Engine 5 | Pre-alpha | Alpha | William Meredith | Yes
| Enemy Respawning | Enemies should respawn if the player respawns at a checkpoint. | Unreal Engine 5 | Pre-alpha | Alpha | William Meredith | Yes
| Ranged Attacks | Ranged Enemies should shoot accurately at the player and stand their ground. The Projectile will be destroyed on collisions. | Unreal Engine 5 | Pre-alpha | Alpha | William Meredith | Yes | Added but needs som small adjustments to projectile.
| Melee Attacks | Melee attacks will be added only to melee enemies. | Unreal Engine 5 | Pre-alpha | Alpha | William Meredith | Yes
| Traversal | Add horizontal and vertical Movement to AI, enemies should be able to persue player once spotted. WITHOUT jumping off of the level. | Unreal Engine 5 | Pre-alpha | Alpha | William Meredith | Yes
Environment | Level Layout | Complete the basic layout of the levels. | Unreal Engine 5 | Pre-alpha | Beta | Nathen Reed | Yes | Created levels 1 and 2, Final/boss level added by Hunter Eck. -Nathen Reed
| Moving Platforms | Moving Floors. | Unreal Engine 5 | Alpha | Beta | Nathen Reed | Yes | Added simple moving platform that ping pongs between two spots. -Nathen Reed
| Wall and Floor Collisions | Create wall and floor segments that will be utilized throughout the levels. Collide with players, projectiles and the Enemies. | Unreal Engine 5 | Pre-alpha | Alpha | Cedrick Lee | Yes | Added accurate collision to current Tilesets.
Design | Player Design | Player characters design and animations. | Unreal Engine 5 | Pre-alpha | Alpha | Hunter Eck | Yes | Rabbit Player model added with flipbook
| Melee Enemy Design | Melee enemy sprites and attack animation. | Unreal Engine 5 | Pre-alpha | Alpha | Hunter Eck | Yes
| Ranged Enemy Design | Ranged enemy AND their projectile. | Unreal Engine 5 | Alpha | Alpha | Hunter Eck | Yes
| Boss Enemy Design | Boss sprite set. | Unreal Engine 5 | Beta | Final Release | Hunter Eck | Yes
| Background Designs | Design of objects behind the levels walls and floors. That arent visually repetitive. | Unreal Engine 5 | Pre-alpha | Final Release | Hunter Eck | Yes
| Collectible Items | Carrot: Ranged, Feather: Double Jump, Arrow: Dash? | Unreal Engine 5 | Alpha | Beta | Hunter Eck | Yes | Added but not currently used any longer as collectables didn’t fit as well.
| Health Pickup | Health Pickup design | Unreal Engine 5 | Alpha | Alpha | Hunter Eck | Yes | Temp floating heart added by Nathen Reed. -Nathen Reed
| Foreground Designs | Design of objects behind the levels walls but in front of the background. | Unreal Engine 5 | Pre-alpha | Alpha | Hunter Eck | Yes
| Level floors and walls | Set of walls and floors that will actually collide with player. | Unreal Engine 5 | Pre-alpha | Alpha | Hunter Eck | Yes

## Test Plan
Test Plan
Repository Link: | https://github.com/OddCardboard/redteam
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution | Last Checked By:
Enemies | output strings and cast to BP_Player to check for valid targetting. Repeatedly test functionality after making any changes. | Fail | Enemy stationary on placement | Added a Print String reading the Movement Mode of the CharacterMovement component every tick. Output was None rather than the expected Walking or Falling. MOVE_None indicates the CharacterMovement component is not running physics; almost always caused by the pawn having no Controller possessing it. Add Movement Input requires a Controller to consume the input and apply movement to the capsule. | Auto Possess AI on BP_MeleeEnemy was set to Spawned. This setting only attaches an AIController to enemies spawned at runtime (i.e., via BP_Spawn_Melee). Enemies placed in the level by hand were never given an AIController, so Add Movement Input calls had nothing to drive the capsule. Set Auto Possess AI (Class Defaults) to Placed in World or Spawned. This covers both placement methods, hand-placed enemies and spawner-spawned enemies, and ensures an AIController is always attached. After the fix, the Movement Mode print output changed from None to Walking, and the enemy began patrolling correctly with WallCheck and LedgeCheck turn-around behavior functioning as intended. | William Meredith (5:47PM, 5/23/2026)
Checkpoints | Repeatedly lower health down to zero to check new spawn locations and use strings to inform new set spawns. | N/A | Player Not getting teleported. | Received errors from respawn event due to the variable used for the spawn transform coming in empty. | Error was caused by player not being passed with the call to the RespawnEvent. Ensuring this was hooked in properly fixed the error. | Nathen Reed (5:39PM, 5/31/2026)
Flipbooks | Repeatedly trigger different animations and double check the logic used. | N/A | enemy turning invisible | sometimes enemy would turn invisibile | Was just a missing flipbook designation. | Nathen Reed (5:39PM, 6/14/2026)
Health | Player health should tick down upon taking damage displayed with a widget or UI Element. | N/A
Boss Class | Use breakpoints and repeated ingame trials checking if logic continues to function correctly. Such as triggering boss ranged attack then triggering charge attack. | N/A
Boss Charge |  | N/A | charge wouldn’t fling and damage the player immediately. | during charge the boss would keep bumping into the player instead of flinging them. | Increased knockback force and extended the attack zone further. | Nathen Reed (5:39PM, 6/14/2026)
Boss Movement |  | N/A | Boss would randomly stop or keep going. | during charage attack the boss wouldn’t halt or would start moving faster without pausing movement. | Fixed by adjusting booleans to record current state more accurately with branches in the movement controls. As well the attack box was clipping the ground slightly due causing it to end charge early. | Nathen Reed (5:39PM, 6/14/2026)
Boss Collision |  | N/A | Player getting blocked by the overlap zone for the stomp attack instead of overlapping and bouncing. | issues with overlapping player and stomp zone | Addded a Slight delay before knockback was applied, and adjusted some of the logic for the hitbox. | Nathen Reed (5:39PM, 6/14/2026)
Player Movement | Repeated testing of controls and movement in testing level. | N/A
Player Attack | Repeated testing of movement with attacks and from different angles. | N/A
Level traversal | traverse between levels repeatedly checking for any camera or control issues. | N/A
Player Game UI | check for discrepancies in player health and the UI display. Check pause menu frequently.